## Project Types
Index | Project | Type | Technology | Number of Story | Stage | Default Stage Time | start time percentage
| Building | Residence | RCC | Single | Preparation | 5 | 0
[5 empty] | SubStructure/ Foundation | 15 | 10 | Start After Preparation
[5 empty] | Super Structure ( Civil Works) | 30 | 0 | Start After SubStructure
[5 empty] | Finishing | 15 | 0 | Start After Super Structure
[5 empty] | Utility and Services ( MEP) | 20 | 20 | Start With Super Structure, Finish With Finishing
[5 empty] | Landscape Works | 10 | 0 | Finish With Finishing
[5 empty] | PunchLists and Handover | 5 | 10 | Start after Finishing
[5 empty] | Overall Project Duration | 100 | 0 | Earliest Start to Latest Finish
Note on F1: ====== ID#AAAAfvGBX2c Sagar Bhusal (2022-09-09 05:23:47) Does Stage depend on Project or any other parameter ?? ------ ID#AAAAfvGBX2g Bipin Gaire (2022-09-09 05:34:19) We may have different stage names for different projects but these are not related to any other parameters in a project. ------ ID#AAAAd0THGdo Sagar Bhusal (2022-09-09 07:28:07) ok thanks

## S-Curve
Revenue S-Curve | Revenue Vs Cost
| Estimated | Actual
X Axis | Time/Duration | Time Duration
Y Axis | Estimated Revenue | Actual Cost
Default Filter
Filter 1 | One Project, Selected Project, or All running projects in a company |  | All Running Projects
Filter 2 | Duration: Selected start or end date, Fiscal Year, Earliest start and Latest Finish date of selected Project |  | Fiscal Year
Filter 3 | Work Item |  | None
Calculations
i. | Estimated Revenue | BOQ Uploaded stretched over time. i.e Item Quantity multiplied by the contract rate
ii. | Actual Cost | Sum of the items below
| a. | Acutal Quanity of Work Done x SubContract Rate (whichever applicable)
| b. | Actual cost of Materials Consumed
| c. | Acutal Cost of Resources consumed
| d. | Actual Cost of Labor Consumed
| e. | Freight/ Transportation Cost
| f. | Admin Cost associated to Project
| g. | Other Costs/Overhead incurred to site ( By account)
| h. | Taxes
Quantity S-Curve | Estimated Quantity Vs Actual Quantity
| Estimated | Actual
X Axis | Time/Duration | Time Duration
Y Axis | Estimated Quantity | Actual Quantity
Default Filter
Filter 1 | One Project, Selected Project, or All running projects in a company |  | All Running Projects
Filter 2 | Duration: Selected start or end date, Fiscal Year, Earliest start and Latest Finish date of selected Project |  | Fiscal Year
Filter 3 | Resource |  | None
Filter 4 | Work Item |  | None
Calculations
i. | Estimated Qty | Estimated Quantity
ii. | Actual Qty | Actual Quantity of Work done

## Contract Type
To Calculate
Type | Description | Manpower | Material | Machine, Equipments etc | Workdone
Contract | when the job is done all complete by the managing company itself. The system has to calculate all the resources. | 1 | 1 | 1 | 1
SubContract (FULL) | When the job is awarded to vendors with all material, resource, Manpower. System only needs to calculate the qty of work done. | 0 | 0 | 0 | 1
Petty Contract | When the job is awarded to vendors with Resources and Manpower. System only needs to calculate the qty of materials used. | 0 | 1 | 0 | 1
Labor Contract (Human resource only) | When the job is awarded to vendors with Manpower. System only needs to calculate the qty of materials and resources used. The billing is done based on the quantity of work. | 0 | 1 | 1 | 1
Labor Supply (Human resource only 2) | When the job is awarded to vendors with Manpower only. System only needs to calculate the qty of materials and resources used. The billing is done based on the manday utilized. | 1 | 1 | 1 | 1

## Item Spec and Norms
Item | Specification | Sub-Spec |  | Unit | Standard Qty for Norms | Keywords | Norms ID
Brick Work | Normal Brick Work | Chimney Brickwork in 1:3 Cement Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:3, 1:3 ratio, 1 3 | CBW13
|  | Chimney Made Brickwork in 1:4 Cement Mortar | Default | CUM | 1 | Brick Masonary made Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:4, 1:4 ratio, 1 4 | CBW14
|  | Chimney Made Brickwork in 1:6 Cement Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:6, 1:6 ratio, 1 6 | BW16
|  | Chimney Made Brickwork with Chun Surkhi in 1:1:1 Chuna Surkhi Sand Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, Chun Surkhhi Sand, surki, chuna, surki sand, First Class Brick Work, English Bond, 1:3, 1:3 ratio, | BWCSS111
|  | Chimney Made Brickwork with Chun Surkhi in 1:2 Chuna Surkhi Mortar |  |  |  |  | BWCS12
|  | Chimney Made Brickwork with mud Mortar |  |  |  |  | BWMM
|  | Machine Made Brickwork in 1:3 Cement Mortar |  | CUM | 1 |  | MBW13
|  | Machine Made Brickwork in 1:4 Cement Mortar | Default | CUM | 1 |  | MBW14
|  | Machine Made Brickwork in 1:6 Cement Mortar |  | CUM | 1 |  | MBW16
Fairface Brick Facade Works
|  | Machine Made Fairface Brick work in 1:4 Cement Mortar | Default | CUM | 1 |  | MFBW14
|  | DachiAppa Brick Work in 1: 4 cement Mortar |  | CUM | 1 |  | DABW14
| RatTrap Bond Brick Work | Machine Made Brickwork in 1:4 Cement Mortar |  | CUM | 1 |  | MBW14
Soling Work | Brick Soling Work |  |  | SM | 1
| Stone Soling Work |  |  | SM | 1
Filling and Compaction Works | Soil Filling and Compaction
Sand Filling and Compaction
Stone Filling and Compaction
Stone Masonary Work | Stone Masonary Work | Stone Masonary Work in 1:3 Cement Sand Mortar
Stone Masonary Work in 1:4 Cement Sand Mortar
Stone Masonary Work in 1:6 Cement Sand Mortar
Dry Stone Masonary Work
Stone Masonary Work in mud Mortar
Block Masonary Work | Concrete Jali Block Masonary
| Hollow Concrete Block | Hollow concrete block work on 1:4 cement sand mortar with 30 m lead.
| Glass Block | Glass Block Work on white cement upto 30 m lead.
Concrete Work
| PCC Works Without Machine |  |  | CUM
|  | 1:4:8 PCC works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1:4:8, ratio, M7 grade Concrete, manual mix, without machine, without mixer | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete,manual mix, without machine, without mixer | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete,manual mix, without machine, without mixer | PCCM15
| PCC for RCC Without Machine |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4, manual mix, without machine, without mixer | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3, manual mix, without machine, without mixer | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2, manual mix, without machine, without mixer | RCCM25
| PCC Works With Machine |  |  | CUM
|  | 1:4:8 PCC works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1:4:8, ratio, M7 grade Concrete, mixture machine, machine, machine mix | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete, mixture machine, machine, machine mix | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete, mixture machine, machine, machine mix | PCCM15
| PCC for RCC Machine |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4, mixture machine, machine, machine mix | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3, mixture machine, machine, machine mix | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2, mixture machine, machine, machine mix | RCCM25
|  | 1:1:2 PCC for RCC Using Plasticizers like microsilica etc |  |  | 1
| PCC Works using RMC |  |  | CUM
|  | 1:4:8 PCC works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1:4:8, ratio, M7 grade Concrete | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete | PCCM15
| PCC for RCC using RMC |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4 | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3 | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2 | RCCM25
Rebar Works | Reinforcement bar Works for RCC | Cutting, bending, placing Reinforcement bars as per design with 30 m overhaul distance for RCC. |  | Metric Ton | 1 | Rebar Works, 10 mm, 12 mm, Dandi, Sairya, Reinforcement works, 16 mm, mm dia bars, stirrups, bending, cutting, binding wire | REWO01
Formwork
Formwork in Column
Formwork in beam, slab, staricase
Formwork in Lintel, sill band
Earthwork | Excavation of Soft Soil
Excavation in Medium Soil
| Excavation in Hard Soil without explosion | Excavation of hard soil using Chisel
Excavation of hard soil without usiing Chisel
Excavation of Soft Soil Using Machine
Excavation Of medium Soil Using Machine
Excavatioin of Hard Soil Using Machine
| Earth Compaction and Filling | Earth Filling and compaction of 15 cm layer
Plaster
Screeding and Punning
Railing Works | SubContract
Iron Works | SubContract
Fixing Door Frames | Petty Contract
Fixing Door Panel | Petty Contract
Paint Works | SubContract
Fixing window | SubContract
Marble Works | Petty Contract
Granite Works | Petty Contract
Tile Works | Petty Contract
Water Proofing Works | SubContract

## Item Spec and Norms For Data En
Item | Specification | Sub-Spec |  | Unit | Standard Qty for Norms | Keywords | Norms ID
Masonary Work | Normal Brick Work | Chimney Made Brickwork in 1:3 Cement Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:3, 1:3 ratio, 1 3 | CBW13
|  | Chimney Made Brickwork in 1:4 Cement Mortar | Default | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:4, 1:4 ratio, 1 4 | CBW14
|  | Chimney Made Brickwork in 1:6 Cement Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, First Class Brick Work, English Bond, 1:6, 1:6 ratio, 1 6 | BW16
|  | Chimney Made Brickwork with Chun Surkhi in 1:1:1 Chuna Surkhi Sand Mortar |  | CUM | 1 | Brick Masonary Work, Brick Wall, Itta, Chun Surkhhi Sand, surki, chuna, surki sand, First Class Brick Work, English Bond, 1:3, 1:3 ratio, | BWCSS111
|  | Chimney Made Brickwork with Chun Surkhi in 1:2 Chuna Surkhi Mortar |  |  |  |  | BWCS12
|  | Chimney Made Brickwork with mud Mortar |  |  |  |  | BWMM
|  | Machine Made Brickwork in 1:3 Cement Mortar |  | CUM | 1 |  | MBW13
|  | Machine Made Brickwork in 1:4 Cement Mortar | Default | CUM | 1 |  | MBW14
|  | Machine Made Brickwork in 1:6 Cement Mortar |  | CUM | 1 |  | MBW16
| Fairface Brick Facade Works | Machine Made Fairface Brick work in 1:4 Cement Mortar | Default | CUM | 1 |  | MFBW14
|  | DachiAppa Brick Work in 1: 4 cement Mortar |  | CUM | 1 |  | DABW14
| RatTrap Bond Brick Work | Machine Made Brickwork in 1:4 Cement Mortar |  | CUM | 1 |  | MBW14
Soling Work | Brick Soling Work |  |  | SM | 1
| Stone Soling Work |  |  | SM | 1
Filling and Compaction Works | Soil Filling and Compaction
Sand Filling and Compaction
Stone Filling and Compaction
Masonary Work | Stone Masonary Work | Stone Masonary Work in 1:3 Cement Sand Mortar
Stone Masonary Work in 1:4 Cement Sand Mortar
Stone Masonary Work in 1:6 Cement Sand Mortar
Dry Stone Masonary Work
Stone Masonary Work in mud Mortar
Masonary Work | Concrete Jali Block Masonary
| Hollow Concrete Block | Hollow concrete block work on 1:4 cement sand mortar with 30 m lead.
| Glass Block | Glass Block Work on white cement upto 30 m lead.
Concrete Work | PCC Works Without Machine | 1:4:8 PCC works |  | CUM | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1 : 4 : 8, ratio, M7 grade Concrete, manual mix, without machine, without mixer | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete,manual mix, without machine, without mixer | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete,manual mix, without machine, without mixer | PCCM15
| PCC for RCC Without Machine |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4, manual mix, without machine, without mixer | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3, manual mix, without machine, without mixer | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2, manual mix, without machine, without mixer | RCCM25
| PCC Works With Machine |  |  | CUM
|  | 1:4:8 PCC works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1:4:8, ratio, M7 grade Concrete, mixture machine, machine, machine mix | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete, mixture machine, machine, machine mix | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete, mixture machine, machine, machine mix | PCCM15
| PCC for RCC Machine |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4, mixture machine, machine, machine mix | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3, mixture machine, machine, machine mix | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2, mixture machine, machine, machine mix | RCCM25
|  | 1:1:2 PCC for RCC Using Plasticizers like microsilica etc |  |  | 1
| PCC Works using RMC |  |  | CUM
|  | 1:4:8 PCC works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 4 8, 1_4_8, 1:4:8, ratio, M7 grade Concrete | PCCM7
|  | 1:3:6 PCC Works | Default |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 3 6, 1_3_6, 1:3:6, ratio, M10 grade Concrete | PCCM10
|  | 1:2:4 PCC Works |  |  | 1 | PCC, PCC Work, PCC only, Concrete only, 1 2 4, 1_2_4, 1:2:4, ratio, M15 grade Concrete | PCCM15
| PCC for RCC using RMC |  |  | CUM
|  | 1:2:4 PCC Works |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M15 Concrete, 1 2 4, ratio, 1_2_4, 1:2:4, Cement 1, Sand 2 Agggregate 4 | RCCM15
|  | 1:1.5:3 PCC For RCC | Default |  | 1 | Concrete Works, RCC Works, PCC For RCC, M20 Concrete, 1 1.5 3, ratio, 1_1.5_3, 1:1.5:3, Cement 1, Sand 1.5 Agggregate 3 | RCCM20
|  | 1:1:2 PCC For RCC |  |  | 1 | Concrete Works, RCC Works, PCC For RCC, M25 Concrete, 1 1 2, ratio, 1_1_2 1:1:2, Cement 1, Sand 1 Agggregate 2 | RCCM25
Rebar Works | Reinforcement bar Works for RCC | Cutting, bending, placing Reinforcement bars as per design with 30 m overhaul distance for RCC. |  | Metric Ton | 1 | Rebar Works, 10 mm, 12 mm, Dandi, Sairya, Reinforcement works, 16 mm, mm dia bars, stirrups, bending, cutting, binding wire | REWO01
Formwork | Formwork in Column
Formwork in beam, slab, staricase
Formwork in Lintel, sill band
Earthwork | Excavation of Soft Soil
Excavation in Medium Soil
| Excavation in Hard Soil without explosion | Excavation of hard soil using Chisel
Excavation of hard soil without usiing Chisel
Excavation of Soft Soil Using Machine
Excavation Of medium Soil Using Machine
Excavatioin of Hard Soil Using Machine
| Earth Compaction | Earth Filling and compaction of 15 cm layer

## Norms
|  |  |  | Manpower |  | Material | [17 empty] | Equipments
Norms Code | Norms | Unit | Standard Qty | Skilled Manpower | Unskilled Manpower | Material 1 | Unit | Qty | Material 2 | Unit | Qty | Material 3 | Unit | Qty | Material 4 | Unit | Qty | Material 5 | Unit | Qty | Material 6 | Unit | Qty | Percentage of Labor | Equipment 1 | Unit | Qty | Equipemnt 2 | Unit | Qty | Equipment 3 | Unit | Qty | Equipment 3 | Unit | Qty
CBW13 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
CBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:4 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.1 | Sand | CUM | 0.27 | Water | Liter | 130
CBW16 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:6 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.07 | Sand | CUM | 0.27 | Water | Liter | 100
MBW13 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
MBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 130
MBW16 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 100
BWCSS111 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:1:1 chuna ( white cement) : Surkhi and sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Chuna ( White Cement) | M.T. | 0.14 | Surkhi | CUM | 0.14 | Sand | CUM | 0.14 | Water | L | 120
BWCS12 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:2 chuna ( white cement) : Surkhi mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Chuna ( White Cement) | M.T. | 0.14 | Surkhi | CUM | 0.28 | Water | Liter | 120
BWMM | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with mud mortar ratio with 30 m lead | CUM | 1 | 1 | 1.7 | Brick | Number | 560 | Mud | CUM | 0.42 | Water | L | 100
MFBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
DABW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
MBW17 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
PCCWM7 | 1:4:8 PCC works | CUM | 1 | 1 | 4 | Cement | MT | 0.17 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.47 | Water | Liter | 100
PCCWM10 | 1:3:6 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.22 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.47 | Water | Liter | 120
PCCWM15 | 1:2:4 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.22 | 10 mm Down Aggregate | Cum | 0.11 | Sand | Cum | 0.445 | Water | Liter | 150
RCCWM15 | 1:2:4 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.22 | 10 mm Down Aggregate | Cum | 0.11 | Sand | Cum | 0.445 | Water | Liter | 150
RCCWM20 | 1:1.5:3 PCC For RCC | CUM | 1 | 0.8 | 7 | Cement | MT | 0.4 | 40 mm Down Aggregate | CUM |  | 20 MM Down Agg | CuM | 0.57 | 10 mm Down Aggregate |  | 0.29 | Sand | Cum | 0.425 | Water | Liter | 200
RCCWM25 | 1:1:2 PCC For RCC | CUM | 1 | 0.8 | 7 | Cement | MT | 0.61 | 40 mm Down Aggregate | CUM |  | 20 MM Down Agg | CuM | 0.64 | 10 mm Down Aggregate |  | 0.21 | Sand | Cum | 0.0425 | Water | Liter | 300
1
PCCM11 | 1:3:6 PCC Works | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.22 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.425 | Water | Liter | 100 |  |  |  |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
PCCM15 | 1:2:4 PCC Works | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.445 | Sand | Cum | 0.445 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
1
RCCM20 | 1:1.5:3 PCC For RCC | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.4 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.445 | Sand | Cum | 0.445 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
RCCM25 | 1:1:2 PCC For RCC | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.61 | 40 mm Down Aggregate | CUM | 0 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.445 | Sand | Cum | 0.445 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
| 1:1:2 PCC for RCC Using Plasticizers like microsilica etc | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.6 | 40 mm Down Aggregate | CUM | 0 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.445 | Sand | Cum | 0.445 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
1
PCCM7 | 1:4:8 PCC works | CUM | 1
PCCM10 | 1:3:6 PCC Works | CUM | 1
PCCM15 | 1:2:4 PCC Works | CUM | 1
1
RCCM16 | 1:2:4 PCC Works | CUM | 1
RCCM21 | 1:1.5:3 PCC For RCC | CUM | 1
RCCM26 | 1:1:2 PCC For RCC | CUM | 1
REWO01 | Cutting, bending, placing Reinforcement bars as per design with 30 m overhaul distance for RCC. | Ton | 1
1
1
1
1
1
1
1
1
1
1
1
1
1
1

## Timeline New Pattern
| Occurance1 |  |  |  |  | Occurance2
Template | Stage | Item | Start Time | End Time | Quantity | Item | Start Time | End Time | Quantity | Default Contract Type
1 | Preparation | Site Clearence | 0 | 100 | 100 |  |  |  |  | Labor-Contract
|  | Site Office Setup | 0 | 100 | 100
|  | As Built Drawing | 0 | 100 | 100
|  | Lab setup | 0 | 100 | 100
|  | Dismantle Works | 0 | 100 | 100
|  | Insurance | 0 | 100 | 100
| SubStructure/ Foundation | Protection | 0 | 10 | 100 |  |  |  |  | Sub-Contract
|  | EarthWork | 10 | 20 | 90 |  |  |  |  | Sub-Contract
|  | Earthwork | 75 | 90 | 95 |  |  |  |  | Sub-Contract
|  | Soling Works | 20 | 25 | 50 | Soling | 90 | 95 | 50 | Petty Contract
|  | Concrete Work | 20 | 25 | 30 | PCC | 90 | 95 | 40 | Petty Contract
|  | Rebar Works | 10 | 40 | 30 |  |  |  |  | Petty Contract
|  | Formworks | 30 | 40 | 15 |  |  |  |  | Sub-Contract
|  | Concrete Work | 30 | 50 | 25 |  |  |  |  | Petty Contract
|  | Masonary Work | 50 | 80 | 20 |  |  |  |  | Petty Contract
|  | DPC Works | 95 | 100 | 100 |  |  |  |  | Petty Contract
|  | Plaster Works | 80 | 90 | 10 |  |  |  |  | Petty Contract
|  | Water Proofing Works | 90 | 95 | 25 |  |  |  |  | Sub-Contract
|  | Earthwork | 10 | 50 | 40 |  |  |  |  | Petty Contract
| Super Structure ( Civil Works) | Screeding and Punning (IPS Flooring) | 85 | 100 | 100 |  |  |  |  | Petty Contract
|  | Concrete Work | 30 | 100 | 45 |  |  |  |  | Petty Contract
|  | Door Frame Installation Works | 50 | 80 | 100 |  |  |  |  | Petty Contract
|  | Rebar Works | 10 | 40 | 30 |  |  |  |  | Petty Contract
|  | Formworks | 30 | 40 | 15 |  |  |  |  | Sub-Contract
|  | Concrete Work | 30 | 50 | 25 |  |  |  |  | Petty Contract
|  | Masonary Work | 50 | 80 | 20 |  |  |  |  | Petty Contract
|  | Plaster Works | 75 | 100 | 80 |  |  |  |  | Petty Contract
|  | Water Proofing Works | 90 | 100 | 75 |  |  |  |  | Petty Contract
| Utility and Services ( MEP) | Electrical Conduiting | 15 | 60 | 100 |  |  |  |  | Petty Contract
|  | Masonary Work | 20 | 50 | 40 |  |  |  |  | Petty Contract
|  | Electrical Wiriing | 60 | 75 | 100 |  |  |  |  | Petty Contract
|  | Electrical Fixtures | 85 | 100 | 95 |  |  |  |  | Petty Contract
|  | Sanitary Pipe Fitting | 30 | 50 | 85 |  |  |  |  | Petty Contract
|  | Sanitary Fixtures | 85 | 100 | 95 |  |  |  |  | Petty Contract
| Landscape Works | Earthwork | 0 | 30 | 10 |  |  |  |  | Sub-Contract
|  | Earthwork | 30 | 50 | 5 |  |  |  |  | Sub-Contract
|  | Masonary Work | 20 | 100 | 30 |  |  |  |  | Petty Contract
|  | Concrete Work | 30 | 40 | 30 |  |  |  |  | Petty Contract
|  | Formworks | 60 | 80 | 5 |  |  |  |  | Sub-Contract
|  | Concrete Work | 70 | 85 | 5 |  |  |  |  | Petty Contract
|  | Masonary Work | 40 | 80 | 20 |  |  |  |  | Petty Contract
|  | Tile Works | 0 | 30 | 10 |  |  |  |  | Petty Contract
|  | Marble Works | 0 | 30 | 10 |  |  |  |  | Petty Contract
|  | Granite Works | 0 | 30 | 10 |  |  |  |  | Petty Contract
|  | Stone Flooring Works | 0 | 30 | 10 |  |  |  |  | Petty Contract
|  | Paint Works | 30 | 80 | 10 |  |  |  |  | Sub-Contract
|  | Plaster Works | 70 | 90 | 10 |  |  |  |  | Petty Contract
|  | Electrical Fixtures | 50 | 100 | 5 |  |  |  |  | Petty Contract
|  | Sanitary Pipe Fitting | 0 | 50 | 15 |  |  |  |  | Petty Contract
|  | Masonary Work | 0 | 100 | 50 |  |  |  |  | Petty Contract
|  | Sanitary Fixtures | 50 | 100 | 5 |  |  |  |  | Petty Contract
| Finishing | Staircase Railing Works | 80 | 100 | 100 |  |  |  |  | Sub-Contract
|  | Earthwork | 20 | 50 | 30 |  |  |  |  | Sub-Contract
|  | Iron Railing Works | 80 | 100 | 100 |  |  |  |  | Sub-Contract
|  | Window Installation | [7 empty] | Sub-Contract
|  | Tile Works | 0 | 50 | 90 |  |  |  |  | Petty Contract
|  | Marble Works | 0 | 50 | 90 |  |  |  |  | Petty Contract
|  | Granite Works | 0 | 50 | 90 |  |  |  |  | Petty Contract
|  | Stone Flooring Works | 0 | 50 | 90 |  |  |  |  | Petty Contract
|  | Wooden Flooring Works | 75 | 100 | 100 |  |  |  |  | Petty Contract
|  | Paint Works | 30 | 80 | 90 |  |  |  |  | Sub-Contract
|  | Door Panel Installation | 60 | 80 | 100 |  |  |  |  | Petty Contract
|  | Soling Works | 0 | 40 | 50 |  |  |  |  | Petty Contract

## Units
Measurement | Standard Unit | Conversion Factor | Local Unit | Terms | Commonly used for following materials
Weight | MT | 20 | 50 kg bag | 50 kg bag | Cement
| MT | 40 | 25 kg Bag | 25 kg Bag
| MT | 1000 | KG | KG, Kilogram | Rebar
| MT | 10 | Bundle | Bundle
| MT | 1 | MT | M.T. , metric ton, metric tons, ton, tons
Volume | CUM | 35.3 | CFT | c.ft. , cubic feet, cu ft, cubic ft., | Aggregate, Sand, Gravel, Rubbel, Stone
| CUM | 0.353 | 100 CFT Mini Truck | 100 CFT Mini Truck
| CUM | 0.13321 | 265 CFT Tipper | 265 CFT Tipper
| CUM | 0.0625 | 10 Wheel Tipper | 10 Wheel Tipper
| CUM | 1 | CUM | CU.M. , cubic m. ,cubic meter,
Area | SM | 10.76 | SF | SF, sq. ft. , sqft, square ft. , square feet, SQF,
| SM | 1 | SM | SM, sq.m. , square m. , square meter , SQM,
Length | M | 3.28 | Ft | Ft, Rft, running feet
| M | 1 | M | M, Rm, meter, meters, runnning meter
Count | Nos | 1 | Nos | number, numbers, no, no.,
| Nos | 1 | Pts | Pts, points
| Nos | 1 | Unit | Unit
| Nos | 1 | Set | Set
| Nos | 1 | job | job
| Nos | 1 | bag | bag
Abbreviation
M | meter
SM | Square Meter
SF | Sqaure Feet
KG | Kilogram
CUM | Cubic Meter
CFT | Cubic Feet
RM | Running Meter
RFT | Running Feet
Nos | Number

## Norms for data entry
|  |  |  | Manpower |  | Material | [17 empty] | Equipments | [9 empty] | Contractors Overhead
Norms Code | Norms | Unit | Standard Qty | Skilled Manpower | Unskilled Manpower | Material 1 | Unit | Qty | Material 2 | Unit | Qty | Material 3 | Unit | Qty | Material 4 | Unit | Qty | Material 5 | Unit | Qty | Material 6 | Unit | Qty | Percentage of Labor | Equipment 1 | Unit | Qty | Equipemnt 2 | Unit | Qty | Equipment 3 | Unit | Qty
CBW13 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
CBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:4 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.1 | Sand | CUM | 0.27 | Water | Liter | 130
CBW16 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:6 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.07 | Sand | CUM | 0.27 | Water | Liter | 100
MBW13 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
MBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 130
MBW16 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 100
BWCSS111 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:1:1 chuna ( white cement) : Surkhi and sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Chuna ( White Cement) | M.T. | 0.14 | Surkhi | CUM | 0.14 | Sand | CUM | 0.14 | Water | L | 120
BWCS12 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:2 chuna ( white cement) : Surkhi mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 560 | Chuna ( White Cement) | M.T. | 0.14 | Surkhi | CUM | 0.28 | Water | Liter | 120
BWMM | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with mud mortar ratio with 30 m lead | CUM | 1 | 1 | 1.7 | Brick | Number | 560 | Mud | CUM | 0.42 | Water | L | 100
MFBW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
DABW14 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
MBW17 | Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
| Brick Work. Supplying preparing and construction of chimney made brick work of approved quality with 1:3 cement sand mortar ratio with 30 m lead | CUM | 1 | 1.5 | 2.2 | Brick | Number | 530 | Cement | M.T. | 0.13 | Sand | CUM | 0.27 | Water | Liter | 150
PCCWM7 | 1:4:8 PCC works | CUM | 1 | 1 | 4 | Cement | MT | 0.17 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.47 | Water | Liter | 100
PCCWM10 | 1:3:6 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.22 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.47 | Water | Liter | 120
PCCWM15 | 1:2:4 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.22 | 10 mm Down Aggregate | Cum | 0.11 | Sand | Cum | 0.445 | Water | Liter | 150
RCCWM15 | 1:2:4 PCC Works | CUM | 1 | 1 | 4 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.22 | 10 mm Down Aggregate | Cum | 0.11 | Sand | Cum | 0.445 | Water | Liter | 150
RCCWM20 | 1:1.5:3 PCC For RCC | CUM | 1 | 0.8 | 7 | Cement | MT | 0.4 | 40 mm Down Aggregate | CUM |  | 20 MM Down Agg | CuM | 0.57 | 10 mm Down Aggregate | Cum | 0.29 | Sand | Cum | 0.425 | Water | Liter | 200
RCCWM25 | 1:1:2 PCC For RCC | CUM | 1 | 0.8 | 7 | Cement | MT | 0.61 | 40 mm Down Aggregate | CUM |  | 20 MM Down Agg | CuM | 0.64 | 10 mm Down Aggregate | Cum | 0.21 | Sand | Cum | 0.0425 | Water | Liter | 300
1
PCCM11 | 1:3:6 PCC Works | CUM | 1 | 0.5 | 3.5 | Cement | MT | 0.22 | 40 mm Down Aggregate | CUM | 0.65 | 20 MM Down Agg | CuM | 0.24 | Sand | Cum | 0.425 | Water | Liter | 100 |  |  |  |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
PCCM15 | 1:2:4 PCC Works | CUM | 1 | 1 | 2 | Cement | MT | 0.32 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.445 | Sand | Cum | 0.445 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
1
RCCM20 | 1:1.5:3 PCC For RCC | CUM | 1 | 2 | 1 | Cement | MT | 0.4 | 40 mm Down Aggregate | CUM | 0.52 | 20 MM Down Agg | CuM | 0.33 | 10 mm Down Aggregate | Cum | 0.5 | Sand | Cum | 0.445 | Water | Liter | 150 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
RCCM25 | 1:1:2 PCC For RCC | CUM | 1 | 0.75 | 4 | Cement | MT | 0.61 | 40 mm Down Aggregate | CUM | 0 | 20 MM Down Agg | CuM | 0.55 | 10 mm Down Aggregate | Cum | 0.6 | Sand | Cum | 0.5 | Water | Liter | 130 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
| 1:1:2 PCC for RCC Using Plasticizers like microsilica etc | CUM | 1 | 0.5 | 2 | Cement | MT | 0.6 | 40 mm Down Aggregate | CUM | 0.2 | 20 MM Down Agg | CuM | 0.34 | 10 mm Down Aggregate | Cum | 0.3 | Sand | Cum | 0.3 | Water | Liter | 143 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
1
PCCM7 | 1:4:8 PCC works | CUM | 1 | 1 | 5 | Cement | MT | 0.4 | 40 mm Down Aggregate | CUM | 0 | 20 MM Down Agg | CuM | 1 | 10 mm Down Aggregate | Cum | 0.6 | Sand | Cum | 0.25 | Water | Liter | 120 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
PCCM10 | 1:3:6 PCC Works | CUM | 1 | 0.5 | 1 | Cement | MT | 0.2 | 40 mm Down Aggregate | CUM | 0.5 | 20 MM Down Agg | CuM | 0.5 | 10 mm Down Aggregate | Cum | 0.8 | Sand | Cum | 0.5 | Water | Liter | 110 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
PCCM15 | 1:2:4 PCC Works | CUM | 1 | 2 | 2 | Cement | MT | 0.7 | 40 mm Down Aggregate | CUM | 0 | 20 MM Down Agg | CuM | 0.7 | 10 mm Down Aggregate | Cum | 0.9 | Sand | Cum | 0.6 | Water | Liter | 100 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
1
RCCM15 | 1:2:4 PCC for RCC Works | CUM | 1 | 0.75 | 4 | Cement | MT | 0.8 | 40 mm Down Aggregate | CUM | 1 | 20 MM Down Agg | CuM | 0.8 | 10 mm Down Aggregate | Cum | 0.4 | Sand | Cum | 0.8 | Water | Liter | 200 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
RCCM20 | 1:1.5:3 PCC For RCC | CUM | 1 | 0.25 | 2 | Cement | MT | 0.9 | 40 mm Down Aggregate | CUM | 4 | 20 MM Down Agg | CuM | 0.9 | 10 mm Down Aggregate | Cum | 0.8 | Sand | Cum | 0.445 | Water | Liter | 400 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
RCCM25 | 1:1:2 PCC For RCC | CUM | 1 | 0.5 | 2.5 | Cement | MT | 0.6 | 40 mm Down Aggregate | CUM | 2 | 20 MM Down Agg | CuM | 0.1 | 10 mm Down Aggregate | Cum | 0.5 | Sand | Cum | 0.55 | Water | Liter | 220 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
REWO01 | Cutting, bending, placing Reinforcement bars as per design with 30 m overhaul distance for RCC. | Ton | 1 | 0.5 | 3.5 | Cement | MT | 0.3 | 40 mm Down Aggregate | CUM | 1.5 | 20 MM Down Agg | CuM | 2 | 10 mm Down Aggregate | Cum | 0.6 | Sand | Cum | 0.67 | Water | Liter | 50 |  | 0.2-0.28 CUM Mixer | Hr | 0.6 | Vibrator | Hr | 0.25 | Diesel | L | 3 | Petrol | L | 0.1
PPW001 | 12.5 mm Plaster 1:2 Cement Sand Ratio Plaster | SM | 100 | 12 | 16 | Cement | MT | 0.9 | Sand | CUM | 1.22
PPW002 | 12.5 mm Plaster 1:3 Cement Sand Ratio Plaster | SM | 100 | 12 | 16 | Cement | MT | 0.625 | Sand | CUM | 1.28
PPW003 | 12.5 mm Plaster 1:4 Cement Sand Ratio Plaster | SM | 100 | 12 | 16 | Cement | MT | 0.538 | Sand | CUM | 1.46
PPW004 | 12.5 mm Plaster 1:6 Cement Sand Ratio Plaster | SM | 100 | 12 | 16 | Cement | MT | 0.382 | Sand | CUM | 1.57
PPW005 | 20 mm Plaster 1:3 Cement Sand Ratio Plaster | SM | 100 | 14 | 19 | Cement | MT | 0.96 | Sand | CUM | 1.95
PPW006 | 20 mm Plaster 1:4 Cement Sand Ratio Plaster | SM | 100 | 14 | 19 | Cement | MT | 0.81 | Sand | CUM | 2.2
PPW007 | 20 mm Plaster 1:6 Cement Sand Ratio Plaster | SM | 100 | 14 | 19 | Cement | MT | 0.57 | Sand | CUM | 2.35
PPW008 | 12.5 mm Cement, Lime and Sand Plaster (1:1:6) |  | 100 | 12 | 16 | Cement | MT | 0.338 | Sand | CUM | 1.37 | Lime/Chuna | CUm | 0.23
PPW009 | 12.5 mm Cement, Lime and Sand Plaster (1:2:12) |  | 100 | 12 | 16 | Cement | MT | 0.18 | Sand | CUM | 1.46 | Lime/Chuna | Cum | 0.24
PPW010 | 12.5 mm Thick Chuna Surkhi plaster (1:2) | SM | 100 | 12 | 16 | Chuna/ Lime | CUM | 0.61 | Surkhi | CUM | 1.22
PPW011 | 1:1 Cement Sand Pointing Works in Brick Works | SM | 100 | 10.5 | 12 | Cement | MT | 0.316 | Sand | CUM | 0.22
PPW012 | 1:2 Cement Sand Pointing Works in Brick Works | SM | 100 | 10.5 | 12 | Cement | MT | 0.21 | Sand | CUM | 0.29
PPW013 | 1:1 Chuna Surkhi Pointing Works in Brick Works | SM | 100 | 10.5 | 12 | Chuna/ Lime | CUM | 0.22 | Surkhi | CUM | 0.22
PPW014 | 1:2 Chuna Surkhi Pointing Works in Brick Works | SM | 100 | 10.5 | 12 | Chuna/ Lime | CUM | 0.15 | Surkhi | CUM | 0.29
PPW015 | Rain Beat / Pani Patti Works | RM | 1 | 0.025 | 0.01 | Cement | MT | 0.007 | Sand | CUM | 0.004 | Waterproof | ml | 0.1
FW001 | 38 mm Screeding Punning ( IPS Flooring) all complete 1:2:4 ratio cement, sand, aggregate | SM | 10 | 1.25 | 2 | Cement | MT | 0.13 | Sand | CUM | 0.18 | 12 mm Aggregate | CUM | 0.36
FW002 | 50 mm Screeding Punning ( IPS Flooring) all complete 1:2:4 ratio cement, sand, aggregate | SM | 10 | 1.25 | 2.5 | Cement | MT | 0.17 | Sand | CUM | 0.23 | 20 mm Aggregate | CUM | 0.46
FW003 | 75 mm Screeding Punning ( IPS Flooring) all complete 1:2:4 ratio cement, sand, aggregate | SM | 10 | 1.25 | 3 | Cement | MT | 0.26 | Sand | CUM | 0.34 | 20 mm Aggregate | CUM | 0.68
FW004 | 20 mm Mosiac Flooring all complete above 20 mm thick 1:2:4 conrete above which 5 mm white cement with marble chips | SM | 10 | 2.5 | 16 | Cement | MT | 0.065 | Sand | CUM | 0.088 | 12 mm Aggregate | CUM | 0.176 | White Cement | MT | 0.061 | 3 mm Marble Chips | CUM | 0.061 | Oxalic Acid | kg | 0.365 | Wax Polish | kg | 0.118 | Tarpein Oi | liter | 0.538
FW005 | 20 mm Terrazzo Flooring all complete above 20 mm thick 1:2:4 conrete above which 5 mm white cement with marble chips | SM | 10 | 2 | 12.6 | Cement | MT | 0.065 | Sand | CUM | 0.088 | 13 mm Aggregate | CUM | 0.176 | White Cement | MT | 0.061 | 4 mm Marble Chips | CUM | 0.061 | Oxalic Acid | kg | 0.365 | Wax Polish | kg | 0.118 | Tarpein Oi | liter | 0.538
FW006 | Porcelein all kinds of Tile Flooring Works All complete | Sm | 10 | 13 | 4.5 | Tile | SM | 11 | Cement | MT | 0.056 | Sand | CUM | 0.152 | White Cement/ Grout | kg | 3.228
FW007 | 16 mm Granite over 20 mm thick 1:2 Cement Sand Mortar all Compelte including Polish | SM | 10 | 2 | 21.5 | 16 mm Granite | SM | 11 | Cement | MT | 0.13 | Sand | CUM | 0.183
FW008 | Marble Flooring Works over cement sand mortar all complete | SM | 10 | 14 | 12 | 16 mm Granite | SM | 11 | Cement | MT | 0.063 | Sand | CUM | 0.128
FW009 | Nosing/ Molding Work Work | RM | 10 | 2.5 | 3.5
FW010 | Marble Polish | Sm | 10 | 0 | 13.5

## Sample BOQ
PROJECT: CONSTRUCTION OF MR. RESIDENCE
SITE:
ABSTRACT OF COST-STRUCTURAL
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
in figure
1 | Site Clearance
| Construction of Temporary shelter for material storage and workers room.Clearing & grubbing of site along with layout of buidling for construction as per drawing specification & instructions. | sq.ft | 1812 | 5 | 9060
2 | Earthwork
2.1 | Earthwork in Excavation
| Earthwork in excavation in trenches, found. In medium clayey soil including dressing of sides, ramming bottom, lift upto 2.0m, disposing of surplus soil. | cub.ft | 4030.79 | 15 | 60461.85
2.2 | Earth Backfilling
| Earthback filling in foundation trenches including watering, consolidating drawing , specification & instructions. | cub.ft | 2821.55 | 15 | 42323.25
2.3 | Earthwork Filling (Plinth filling)
| Earthback filling in foundation trenches including watering, consolidating drawing , specification & instructions. | cub.ft | 3495.88 | 15 | 52438.2
2.4 | Sand Filling
| Sand filling in Plinth under floors of 50mm thick including watering, consolidating and dressing complete as per drawing, specification & instruction | c.ft. | 142.66 | 35 | 4993.1
3 | PCC Works
| Providing, mixing and placing 75mm thick PCC (1:3:6) using PPC Cement equivalent in foundation trenches and plinths. | cub.ft | 441.7 | 360 | 159012
4 | Brickworks
4.1 | Providing and laying local chimney made brick in one layer dry flat brick soling with sand sealing and mechanical compaction all complete. | sq.ft | 1519.85 | 75 | 113988.75
4.2 | In c/s (1:4) in foundation in local chimney made bricks | cft | 750 | 450 | 337500 | Perimeter Wall Only
5 | Concrete works
| Providing, mixing, placing, compacting and curing for seven days PCC for RCC works including centering with reinforcements all completes as per drawing, specification and instruction. |  |  |  |  | HETAUDA/ ARGAKHACHI/SHIVAM/H ONGHI OR equivalent
5.1 | In foundation M20 using opc cement | c.ft | 895.69 | 500 | 447845
5.2 | In superstructure M20 ( 1:1.5:3 ) opc cement | c.ft | 1973.59 | 500 | 986795
6 | Reinforcement Steel
| Providing and fixing reinforcement (Fe500) confirming to IS code in all beams, column, slabs, lintels, chajja, staircase, DPC, Corners, T-junction, counter table etc. as per detail drawings and specifications including straightening, ending, placing and binding in proper directed by engineer and including transporting of material upto 30m lead all complete work using rebar equivalent. | kg | 15412.15 | 135 | 2080640.25 | Panchakanya or any equivalent to it
7 | Centering and Shuttering of Formwork
| Centering and Shuttering of Formwork(12mm thick water proof coloured ply board) | sq.ft | 6980.44 | 75 | 523533
ABSTRACT OF COST - WALLS AND PLASTERS
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
in figure
1 | Brickworks
1.1 | In c/s (1:4) in superstructure in local chimney made first class bricks(9") | cft | 2194.82 | 500 | 1097410
1.2 | In c/s (1:4) in superstructure in local chimney made first class bricks(4") | sq.ft | 1279.6 | 300 | 383880
2 | Plastering Works
2.1 | Plastering with specified mortar mix ratio in any level, size and shape of wall, ceiling, band, blocks etc. as required including racking, watering cleaning of base , plastering to plumb, line, level, smoothness etc. and including curing and cost of necessary scaffoldings works all complete as per drawings and specifications. |  |  |  |  | HETAUDA/ ARGAKHACHI/SHIVAM/ HONGSHI OR equivalent
2.1.1 | A) 20 mm thick C/S (1:6) plaster on external walls | sq.ft | 3965.18 | 70 | 277562.6
2.1.2 | B) 12.5 mm thick C/S (1:4) plaster on internal walls | sq.ft | 5808.9 | 60 | 348534
3 | Doors and Windows
3.1 | Wooden Door
3.1.1 | Supplying and fixing wooden frame (NEPALI AGRAK)with necessary fittings all complete | Cft | 37.14 | 7500 | 278550
ABSTRACT OF COST- FINISHING WORKS
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
in figure
1 | Finishing Works
1.1 | Plastering with specified mortar mix ratio in any level, size and shape of wall, ceiling, band, blocks etc. as required including racking, watering cleaning of base , plastering to plumb, line, level, smoothness etc. and including curing and cost of necessary scaffoldings works all complete as per drawings and specifications. |  |  |  |  | HETAUDA/ ARGAKHACHI/SHIVAM/H ONGSHI OR equivalent
1.1.2 | c) cornices and panipatti designs on windows & PROJECTION EDGES | r.ft. | 529.5 | 120 | 63540
2 | Flooring Works |  |  |  | 0
2.1 | Supplying and laying IPS flooring works all complete (Flooring Type F1) as per drawing, specification and instruction. (BEDROOMS, ROOM AND STORAGE) | sq.ft | 765.9 | 125 | 95737.5
2.3 | Supplying and laying of Granite in all the staircase steps , ENTRANCE STAIRS and landing (Flooring Type F3) as per drawing, specification and instruction. | sq.ft | 252.62 | 550 | 138941 | 16mm Thick.; BASE RATE= 350
2.4 | Supplying and Laying Porecelyne Non Glaze Tile with 1:4 Cement Sand Mortar with Border for TOILETS / BATHROOMS (Flooring Type-F2)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) (IN ALL TOILETS/ BATHROOMS) | sq.ft | 159.1 | 400 | 63640 | Base rate of tile are about 180 per sqft. (SIZE: 12"x 12" )
2.5 | Supplying and Laying Porecelyne Non Glaze Tile with 1:4 Cement Sand Mortar with Border for INTERIOR ROOMS FLOORS (Flooring Type-F4)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) (IN LIVING ROOM, PASSAGE, PUJA ROOM, KITCHEN) | sq.ft | 605.22 | 420 | 254192.4 | Base rate of tile are about 200 per sqft. (SIZE: 24"x 24" )
2.6 | Supplying and Laying Porecelyne Non Glaze Tile with 1:4 Cement Sand Mortar with Border for TERRACES, VERANDHA FLOORS (Flooring Type-F5)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) | sq.ft | 1063.12 | 400 | 425248 | Base rate of tile are about 180 per sqft. (SIZE: 12"x 12" )
2.7 | Supplying and Laying Porecelyne Non Glaze HIGH GVT Tile with 1:4 Cement Sand Mortar with Border for CAR PORCH FLOOR (Flooring Type-F7)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) | sq.ft | 163 | 450 | 73350 | Base rate of tile are about 230 per sqft. (SIZE: 12"x 12" )
2.8 | Supplying and Laying Porecelyne Non Glaze Tile with 1:4 Cement Sand Mortar with Border for TOILETS / BATHROOMS & KITCHEN , PUJA ROOM (WALLS)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) | sq.ft | 1199.01 | 400 | 479604 | Base rate of tile are about 180 per sqft. (SIZE: 12"x 18" )
2.9 | GRANITE works below windows and on parapet walls | Sqft | 336.95 | 140 | 47173 | (11" wide in windows; 11" wide in parapets)
11 | WATERPROOFING WORKS
10.4 | Applying and laying two coats of water proofing chemicals like Dr. Fixit as per instructions by engineer. ( IN TOILET/BATHROOMS ,TERRACES AND BALCONIES TILE SURFACES) | sq.ft | 2927.89 | 100 | 292789 | water proofing chemical of Dr. Fixit or Perma
11 | Skirting
11.1 | Supplying and laying IPS SKIRTING works all complete (Flooring Type F1) as per drawing, specification and instruction. (BEDROOMS, ROOM AND STORAGE) | R.ft | 299 | 75 | 22425 | 6" high skirting
11.2 | Supplying and laying IPS SKIRTING works with Laminated Wooden Parquet SKIRTING Finish all complete (Flooring Type F6) as per drawing, specification and instruction. (IN VISITOR'S ROOM, BEDROOMS, OFFICE AND FAMILY ROOM) | R.ft | 315.75 | 235 | 74201.25 | 6" high skirting
10.3 | Supplying and laying of Granite SKIRTING in all the staircase steps , ENTRANCE STAIRS and landing (Flooring Type F3) as per drawing, specification and instruction. | R.ft | 71.05 | 550 | 39077.5 | 6" high skirting
10.1 | Supplying and Laying Porecelyne Non Glaze Tile SKIRTING with 1:4 Cement Sand Mortar with Border for INTERIOR ROOMS FLOORS (Flooring Type-F4)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) (IN LIVING ROOM, PASSAGE, PUJA ROOM, KITCHEN) | R.ft | 194.42 | 300 | 58326 | 6" high skirting
10.1 | Supplying and Laying Porecelyne Non Glaze Tile SKIRITNG with 1:4 Cement Sand Mortar with Border for TERRACES, VERANDHA, FLOORS (Flooring Type- F5)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) | R.ft | 240.5 | 250 | 60125 | 6" high skirting
10.1 | Supplying and Laying Porecelyne Non Glaze HIGH GVT Tile with SKIRTING 1:4 Cement Sand Mortar with Border for CAR PORCH FLOOR (Flooring Type- F7)all complete.(SOMANY,KAJJARIA , NITCO OR EQUIVALENT BRAND) | R.ft | 40.2 | 300 | 12060 | 6" high skirting
11 | MOULDING/ NOSING WORKS
11.1 | Moulding or Nosing works in Granite edges in skirting and tops all complete | R.ft | 590.14 | 100 | 59014 | SINGLE MOULDING
12 | Doors and Windows
12.1 | Wooden Door
2012-01-02 | Supplying and providing DOOR shutters with full panel including fittings and transportation | Sqft | 308 | 650 | 200200
2012-01-02 | Supplying, Providing & Fixing Aesthetically carved Wooden DOOR with full panel including fittings and transportation all complete (Size= 5' x7') | nos. | 1 |  |  | Can be only If the Design is Provided
12.2 | UPVC windows/doors
2012-02-01 | Supplying and providing UPVC Sliding/SWINGING WINDOWS including fittings and transportation | sq.ft | 351 | 900 | 315900
2012-02-02 | Supplying and providing UPVC Sliding DOORS including fittings and transportation | sq.ft | 42 | 900 | 37800
2012-02-03 | Supplying and providing UPVC FIXED DOORS / WINDOWS including fittings and transportation | sq.ft | 104 | 900 | 93600
2012-02-04 | Supplying and providing 10mm square rods fabricated metal grills in Ground Floor windows including fittings and transportation | sq.ft | 168.3 | 300 | 50490
13 | Painting Works
13.1 | Supplying and painting the interior wall surface with Luxury emulsion paint of approved brand and uniform shade including primer all complete as per instructed by engineer. | sq.ft | 4609.9 | 40 | 184396
13.2 | Supplying the interior wall and ceiling surface with 2mm white putty plaster all complete as per instructed by engineer . | sq.ft | 6507.57 | 30 | 195227.1
13.3 | Supplying and painting the exterior wall surface with two coat of weather coat (APEX ULTIMA or Equivalent) paint of approved brand and uniform shade including primer. | sq.ft | 3965.18 | 40 | 158607.2 | whole external faces of building except claddings
14 | IRON WORKS/RAILING WORKS |  |  |  | 0
14.1 | Supplying and Providing Railings with SS metal posts and wooden hand-rests (3.28FT.=1000mm HIGH) IN ALL STAIRCASE with all necessary fittings and transportation | R.ft | 40.14 | 3000 | 120420
14.2 | Supplying and Providing METAL L-SHAPED staircase with all necessary fittings and transportation | kg | 300 | 250 | 75000
14.3 | Supplying and Providing 10 mm thick TOUGHENED GLASS WORKS IN TERRACE AND BALCONY, with all necessary fittings and transportation | S.FT | 414.92 | 1500 | 622380
14.4 | Supplying and Providing METALwater tank stand at terrace with all necessary fittings and transportation | unit | 1 | 35000 | 35000
15 | CLADDING WORKS |  |  |  | 0
15.1 | Supplying and laying STONE TEXTURED TILE CLADDING ON exterior walls | sq.ft. | 407.12 | 500 | 203560 | TILE SIZE= 24"X12"
16 | BORING |  |  |  | 0
16.1 | Installtion of Boring Water source or Well | set | 1 |  |  | As per Actual
17 | TOILET CABINET WORKS |  |  |  | 0
17.1 | Supplying and laying of Granite in all the Toilet basin counters including skirtings as per drawing, specification and instruction. | sft | 109.88 | 500 | 54940 | for 5 toilets
17.2 | Granite Mouldngs in all the Toilet basin counters as per drawing, specification and instruction. | rft | 124.5 | 100 | 12450 | for 5 toilets
17.3 | Supplying and fixing wooden furniture basin cabinet in each toilet as per specification and drawings | sft | 41.25 | 2500 | 103125 | for 5 toilets
ABSTRACT OF COST- WT; ST; SP
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
in figure
| UNDERGROUND WATER TANK |  |  |  |  | Under water tank have the capacity of around 15000 litre .
17 | Earthwork in excavation in water tank, found. In medium clayey soil including dressing of sides, ramming bottom, lift upto 2.0m, disposing of surplus soil. | c.ft | 1125.56 | 0 | 0
18 | Providing and laying local chimney made brick in one layer dry flat brick soling with sand sealing and mechanical compaction all complete. | sq.ft | 182 | 65 | 11830
19 | Providing, mixing and placing 75mm thick PCC (1:3:6) using PPC cement in water tank. | c.ft | 45.5 | 350 | 15925
20 | In water tank M20 using OPC cement or any equivalent. | c.ft | 282.25 | 500 | 141125
21 | Providing and fixing reinforcement (Fe500) of Panchakanya Brand confirming to IS code in all beams, column, slabs, lintels, chajja, staircase, DPC,Shear wall, Comers, T-junction, counter table etc. as per detail drawings and specifications including straightening, ending, placing and binding in proper directed by engineer and including transporting of material upto 30m lead all complete work using Panchakanya rebar or equivalent. | kg | 790.53 | 135 | 106721.55
FORMWORK
| Formwork , centering and shuttering with water proofing plywoood for all kinds of R.C.C works of any shape, size and at any level with necessary propping, scaffoling, staging , supporting, cutting holes for utilization works etc | Sqft | 645.75 | 75 | 48431.25
22 | Supplying and laying IPS works with cemend: sand ratio of 1:2:4 with all completeusing specified PPC cement as per drawing, specification and instruction. | sq.ft | 368.75 | 125 | 46093.75
23 | 12.5 mm thick C/S (1:4) plaster on internal walls | sq.ft | 225 | 60 | 13500
24 | Applying and laying two coats of waterproofing chemical in water contact area with cement sand mixtures(Dr. fixit &Perma). | sq.ft | 368.75 | 100 | 36875 | water proofing chemical of Dr. Fixit or Perma
| SEPTIC TANK |  |  |  |  | Septic tank have a holding capacity of around 3000 litre of waste.
25 | Earthwork in excavation in Septic tank, found. In medium clayey soil including dressing of sides, ramming bottom, lift upto 2.0m, disposing of surplus soil. | c.ft | 288 | 15 | 4320
26 | Providing and laying local chimney made brick in one layer dry flat brick soling with sand sealing and mechanical compaction all complete. | sq.ft | 48 | 65 | 3120
27 | Providing, mixing and placing 75mm thick M10 PCC (1:3:6) using PCC cement equivalent in Septic tank. | c.ft | 12 | 360 | 4320 | HETAUDA/ SHIVAM equivalent
28 | In c/s (1:4) in septic tank in local chimney made bricks(9") | c.ft | 89.25 | 420 | 37485
28.1 | In c/s (1:4) in septic tank in local chimney made bricks(4") | sq.ft | 32 | 540 | 17280
29 | In septic tank M20 using cement or any equivalent cement. | c.ft | 20.63 | 540 | 11140.2
REINFORCEMENT STEEL
30 | Providing and fixing reinforcement (Fe500) of Panchakanya Brand confirming to IS code as per detail drawings and specifications including straightening, ending, placing and binding in proper directed by engineer and including transporting of material upto 30m lead all complete work using Panchakanya/ Himal rebar or equivalent. | kg | 32.6 | 135 | 4401 | Panchakanya or Equivalent
30.1 | FORMWORK |  |  |  | 0
|  | Sqft | 41.25 | 75 | 3093.75
31 | Supplying and laying IPS works with cement: sand ratio of 1:2:4 with all completeusing specified PPC cement as per drawing, specification and instruction. | sq.ft | 124 | 125 | 15500
32 | 12.5 mm thick C/S (1:4) plaster on internal walls | sq.ft | 100 | 60 | 6000
SOAK PIT
33 | Earthwork in excavation in Soak pit, found. In medium clayey soil including dressing of sides, ramming bottom, lift upto 2.0m, disposing of surplus soil. | c.ft | 21.21 | 15 | 318.15
34 | Providing and laying local chimney made brick in one layer dry flat brick soling with sand sealing and mechanical compaction all complete. | sq.ft | 7.07 | 65 | 459.55
35 | Providing, mixing and placing 75mm thick PCC (1:3:6) using PCC Cement equivalent in Soak pit. | c.ft | 1.77 | 350 | 619.5 | HETAUDA/ SHIVAM equivalent
36 | In c/s (1:4) in soak pit in local chimney made bricks(4") | sq.ft | 28.29 | 500 | 14145
37 | In soakpit M20 using Cement or any equivalent. | c.ft | 2.97 | 500 | 1485 | HETAUDA/ SHIVAM equivalent
38 | Providing and fixing reinforcement (Fe500) confirming to IS code in septic tank as per detail drawings and specifications including straightening, ending, placing and binding in proper directed by engineer and including transporting of material upto 30m lead all complete work using Panchakanya/ Himal rebar or equivalent. | kg | 4.6 | 140 | 644
39 | Supplying and laying IPS works with cement: sand ratio of 1:2:4 with all completeusing specified PPC cement as per drawing, specification and instruction. | sq.ft | 7.1 | 125 | 887.5
40 | 12.5 mm thick C/S (1:4) plaster on internal walls | sq.ft | 28.29 | 60 | 1697.4
ABSTRACT OF COST OF BOUNDARY WALL
S.N. | Description of works | Unit | Quantity | Rate (NRs) | Amount (NRs) | Remarks
in figure
1 | EXCAVATION WORK
| Earthwork in excavation in trenches, found. In medium clayey soil including dressing of sides, ramming bottom, lift upto 2.0m, | Cu.ft | 1122.19 | 15 | 16832.85
1.2 | Earth Backfilling
| Earthback filling in foundation trenches including watering, consolidating drawing , specification & instructions. | cub.ft | 673.31 | 0 | 0
2 | PCC Works
| Providing, mixing and placing 75mm thick | cub.ft | 62.34 | 250 | 15585
3 | Brickworks
3.1 | Providing and laying local chimney made brick in one layer dry flat brick soling with sand sealing and mechanical compaction all complete. | sq.ft | 174.56 | 65 | 11346.4
3.2 | In c/s (1:4) in local chimney made bricks below the ground | cft | 0 | 400 | 0
3.3 | In c/s (1:4) in local chimney made bricks above the ground | S.Ft | 460 | 350 | 161000
4 | RCC WORK
| RCC work of mix 1:1.5:3 above the boundary wall and Gate posts | cuft. | 56.67 | 500 | 28335
5 | FORMWORK | Sqft | 108.88 | 75 | 8166
6 | METAL RAILING POST (3/4" CI square pipes ) | sq.ft. | 131.63 | 250 | 32907.5
7 | PLASTERING 20MM TH. ON BOTH SIDES OF BOUNDARY WALL | sq.ft. | 1053 | 65 | 68445
7 | Stone Textured Wall Paint | sq.ft. | 1053 | 75 | 78975
8 | Rebar work | Kg. | 263.81 | 135 | 35614.35
9 | Metal Entrance Gates | s.ft | 72 | 900 | 64800
10 | Boundary Wall Lamps | nos. | 5 | 1000 | 5000
11 | Electrical Works for Boundary wall (@ 5% of total civil works in boundary) | LS | 1 | 7500 | 7500
12 | Stone Masonary Wall Below Existing Front Road Level ( 1.5 ft wide, 2 ft below Existing GF, 4 Ft upto Road leve | CFT | 981 | 250 | 245250

## TASK( Ignore)
Stage | Major Item | Task | Specfication
Sub Structure | BrickWork | Brick Soling for Foundation pad and Strap Beam
Sub Structure | BrickWork | Brick Soling For Tie Beam
Sub Structure | BrickWork | 9 inch brick wall above tie Beam
Sub Structure | BrickWork | Stepped Brick Work for Toe Wall
Super Structure 1 | BrickWork | Brick Soling for Ground Floor PCC
Super Structure 1 | BrickWork | Masonary Work upto Sill Level Ground Floor
Super Structure 1 | BrickWork | Masonary Work Above Sill Level upto Lintel Level (Ground Floor)
Super Structure 1 | BrickWork | Masonary Work Above Lintel Band (Ground Floor)
Super Structure 2 | BrickWork | Masonary Work upto Sill Level (First Floor)
Super Structure 2 | BrickWork | Masonary Work Above Sill Level upto Lintel Level (First Floor)
Super Structure 2 | BrickWork | Masonary Work Above Lintel Band (First Floor)
Super Structure 3 | BrickWork | Masonary Work upto Sill Level (Second Floor)
Super Structure 3 | BrickWork | Masonary Work Above Sill Level upto Lintel Level (Second Floor)
Super Structure 3 | BrickWork | Masonary Work Above Lintel Band (Second Floor)
Super Structure 3 | BrickWork | Masonry Work for Parapet Wall on applicable floors
Sub Structure | BrickWork | Brick Soling for Water Tank
Sub Structure | BrickWork | Brick Work For Water Tank
Sub Structure | BrickWork | Brick Soling For Septic Tank
Sub Structure | BrickWork | Brick Work For Septic Tank
Final | Cleaning Works | Cleaning and Handover
Sub Structure | ConcreteWork | PCC For Foundation Pad and Strap Beam
Sub Structure | ConcreteWork | Rebar Cutting And Bending for Foundation, Column Strap Beam
Sub Structure | ConcreteWork | Foundation mat placement
Sub Structure | ConcreteWork | Column Placement
Sub Structure | ConcreteWork | Foundation Concrete Work
Sub Structure | ConcreteWork | Tie Beam Rebar Cutting and Bending
Sub Structure | ConcreteWork | Tie Beam Rebar Placement
Sub Structure | ConcreteWork | Tie Beam Formwork
Sub Structure | ConcreteWork | Tie Beam Concreting
Sub Structure | ConcreteWork | Plinth Beam Rebar Cutting and Bending
Sub Structure | ConcreteWork | Plinth Beam Rebar Placement
Sub Structure | ConcreteWork | Plinth Beam Formwork
Sub Structure | ConcreteWork | Plinth Beam Concreting
Super Structure 1 | ConcreteWork | 1:2:4 PCC Work in Ground Floor Slab
Sub Structure | ConcreteWork | Rebar Cutting and Bending For column
Sub Structure | ConcreteWork | Rebar Placement for column
Super Structure 1 | ConcreteWork | Form Work For Column ( Ground Floor)
Super Structure 1 | ConcreteWork | Concreting of Column (Ground Floor)
Super Structure 1 | ConcreteWork | Form Work of Sill band (Ground Floor)
Super Structure 1 | ConcreteWork | Sill Band (Ground Floor)
Super Structure 1 | ConcreteWork | Form Work of Lintel band (Ground Floor)
Super Structure 1 | ConcreteWork | Lintel Band (Ground Floor)
Super Structure 1 | ConcreteWork | FormWork for First Floor Slab
Super Structure 1 | ConcreteWork | Rebar Cutting and Bending for First Floor Slab
Super Structure 1 | ConcreteWork | Concreting on First Floor Slab
Super Structure 2 | ConcreteWork | Form Work For Column First Floor
Super Structure 2 | ConcreteWork | Concreting of Column (First Floor)
Super Structure 2 | ConcreteWork | Sill Band (First Floor)
Super Structure 2 | ConcreteWork | Lintel Band (First Floor)
Super Structure 2 | ConcreteWork | FormWork for Second Floor Slab
Super Structure 2 | ConcreteWork | Rebar Cutting and Bending for Second Floor Slab
Super Structure 2 | ConcreteWork | Concreting on Second Floor Slab
Super Structure 3 | ConcreteWork | Form Work For Column (Second Floor)
Super Structure 3 | ConcreteWork | Concreting of Column (Second Floor)
Super Structure 3 | ConcreteWork | Sill Band (Second Floor)
Super Structure 3 | ConcreteWork | Lintel Band (Second Floor)
Super Structure 3 | ConcreteWork | FormWork for Third Floor Slab
Super Structure 3 | ConcreteWork | Rebar Cutting and Bending for Third Floor Slab
Super Structure 3 | ConcreteWork | Concreting on Third Floor Slab
Sub Structure | ConcreteWork | PCC For Water Tank
Sub Structure | ConcreteWork | PCC for Septic Tank
Sub Structure | ConcreteWork | Concreting for Water Tank Side Wall
Sub Structure | ConcreteWork | Rebar Cutting and Bending for Water Tank
Sub Structure | ConcreteWork | Formwork For Water Tank Side
Sub Structure | ConcreteWork | Formwork For Water Tank Slab
Sub Structure | ConcreteWork | Rebar Cutting, Bending and Placing for Water tank Slab
Sub Structure | ConcreteWork | Concreting for Water Tank Slab
Sub Structure | ConcreteWork | Conrete Works for Septic Tank Slab
Sub Structure | ConcreteWork | Water Proofing For Water Tank
Sub Structure | ConcreteWork | Plaster And punning for Water Tank
Sub Structure | ConcreteWork | Plaster and Punning for Septic Tank
Super Structure 1 | ConcreteWork | Kitchen Counter Slab ( Whichever Floor)
Sub Structure | ConcreteWork | Facia
Sub Structure | ConcreteWork | Sunken slab
Sub Structure | ConcreteWork | Chajja
Sanitary Works | construction of Manhole with Manhole Cover | Manhole
Finishing | Cornice Works | Cornice
External work | dome light on gate post | dome light on gate post
Finishing | Door Panel Fittings | Door Panel Fittings
Super Structure 1 | Door Window | Fixing Door Window Frame Ground Floor
Super Structure 2 | Door Window | Fixing Door Window Frame(First Floor)
Super Structure 3 | Door Window | Fixing Door Window Frame (Second Floor)
Electrical Works | Earthing | Earthing
Sub Structure | Earthwork | Foundation Excavation
Sub Structure | Earthwork | Removal of Earth
Sub Structure | Earthwork | Excavation for lower Tie Beam
Sub Structure | Earthwork | Excavation for Toe Wall
Sub Structure | Earthwork | Excavation for Water Tank
Sub Structure | Earthwork | Excavation for Septic Tank
Sub Structure | Earthwork | Excavation for Soak Pit
Sub Structure | Earthwork | Filling of Earth upto Plinth Level
Sub Structure | Earthwork | Earth Filling Compaction after Plinth Beam Casting
Electrical Works | Electrical Cables Fixing for First Floor Wall | Electrical Cables Fixing for First Floor Wall
Electrical Works | Electrical Cables Fixing for Ground Floor Wall | Electrical Cables Fixing for Ground Floor Wall
Electrical Works | Electrical Cables Fixing for Second Floor | Electrical Cables Fixing for Second Floor
Electrical Works | Electrical Pipe layout and Box Fixing for First Floor Wall | Electrical Pipe layout and Box Fixing for First Floor Wall
Electrical Works | Electrical Pipe Layout and Box Fixing for Second Floor | Electrical Pipe Layout and Box Fixing for Second Floor
Electrical Works | Electrical Pipe Wiring | Electrical Pipe Wiring Layout First Floor Slab
Electrical Works | Electrical Pipe Wiring | Electrical Pipe Wiring Layout Second Floor Slab
Electrical Works | Electrical Pipe Wiring | Electrical Pipe Wiring Layout Third Floor Slab
Electrical Works | Electrical Pipe Wiring | Electrical Pipe layout and Box Fixing for Ground Floor Wall
Final | Exterior Boundry Wall | Exterior Boundry Wall
External work | External boundary | External boundary
Final | External Flooring and Fininshing | External Flooring and Fininshing
Electrical Works | External pipe wirring | External pipe wirring
External work | filling and levelling | filling and levelling
Electrical Works | Fixing Lighting fixtures | Fixing Lighting fixtures
Final | Fixing Over Head Water Tank | Fixing Over Head Water Tank
Electrical Works | Fixing Switches and Boards | Fixing Switches and Boards
Finishing | Fixing Window | Fixing Window
Final | Gate Fixing | Gate Fixing
External work | gate post | gate post
External work | Laundry and Tap | Laundry and Tap
Finishing | Marble Works | Marble Works on StairCase
Finishing | Marble Works | Marble Works on KItchen Slab, Entrance Steps and Misc
Finishing | Marble Works | Marble in sill and parapet
Electrical Works | Meter box | Meter box
Finishing | Paint Work | Paint Works
Finishing | Parapet Railing Works | Parapet Railing
External work | Paving block | Paving block
External work | Peti and steps | Peti and steps
Sanitary Works | Pipe work for sewer and Manhole | Pipe work for sewer and Manhole
Sanitary Works | Pipe works in external | Pipe works in external
Final | Placing Circular Staircase | Placing Circular Staircase
Super Structure 1 | Plaster | Ground Floor Internal Plaster
Super Structure 1 | Plaster | Ground Floor Ceiling Plaster
Super Structure 1 | Plaster | Ground Floor External Plaster
| Plaster | Pani Pati
| Plaster | Sill lintel decoration
| Plaster | Design or groving plaster
| Plaster | Parapet Spring wall plaster
Super Structure 2 | Plaster | First Floor Internal Plaster
Super Structure 2 | Plaster | First Floor Ceiling Plaster
Super Structure 2 | Plaster | First Floor External Plaster
Super Structure 3 | Plaster | Second Floor Internal Plaster
Super Structure 3 | Plaster | Second Floor Ceiling Plaster
Super Structure 3 | Plaster | Second Floor External Plaster
Sanitary Works | Plumbing Pipe Fixing For First Floor | Plumbing Pipe Fixing For First Floor
Sanitary Works | Plumbing Pipe Fixing For Second Floor | Plumbing Pipe Fixing For Second Floor
Sanitary Works | Plumbing Pipe Fixing Ground Floor | Plumbing Pipe Fixing Ground Floor
Preparations | Preparations | Site Clearance
Preparations | Preparations | Foudation Layout
Preparations | Preparations | Labor Quarter Construction
Preparations | Preparations | Storage Site Fixing
Preparations | Preparations | Water Source (Well)
Preparations | Preparations | Electricity Source Finalization
Preparations | Preparations | All drawing sets
Preparations | Preparations | Fencing where possible
Sanitary Works | Pressure test | Pressure test
Sanitary Works | Sanitary Fixtures | Sanitary Fixtures
Sanitary Works | Sanitary Fixtures | Sanitary Fixtures
Sub Structure | Sanitary Works | Fixing Sewer and Soil line (Under Ground)
Finishing | Screeding and Punning | Screeding and Punning on Floor (on all Stories)
External work | slope for car poarch | slope for car poarch
Finishing | Staircase Railing Works | StairCase Railing
Finishing | Tile Works | Tile Work on all Floors
Finishing | Tile Works | Elevation Tile Work on all Bathroom
Finishing | Tile Works | Elevation Tile on Kitchen
Sanitary Works | Water tank Fitting | Water tank Fitting
Finishing | Window Grill | Window Grill

## My Timeline
Occurance1
Stage | Iten | Start Time | End Time | Quantity
Preparations | Site Clearence | 0 | 100 | 100
SubStructure | Brick Work | 0 | 10 | 100
SuperStructure | Brick Work | 85 | 100 | 100
Finishing | Stone Masonary Work | 80 | 100 | 100
Utility and Servcies | Soling Work | 15 | 60 | 100
Landscape | Filling and Compaction Works | 0 | 30 | 100
PunchLists and Handover | Stone Masonary Work | 90 | 100 | 100
Preparation | 5%
SubStructure | 15%
Super Structure | 30%
Finishing | 25%
Utility and Services | 10%
Landscape | 10%
PunchLists and Handover | 5%

## Timeline
| Occurance |  |  |  | Occurance2 |  |  |  | Occurance3
Item | Stage | Start Time | End Time | Quantity | Stage | Start Time | End Time | Quantity | Stage | Start Time | End Time | Quantity
Site Clearence | Preparations | 0 | 100 | 100
Protection | SubStructure | 0 | 10 | 100
Excavation | SubStructure | 10 | 20 | 90 | Landscape | 0 | 30 | 10
EarthFilling and Compaction | SubStructure | 75 | 90 | 95 | Landscape | 30 | 50 | 5
Soling | SubStructure | 20 | 25 | 50 | SubStructure | 90 | 95 | 50
PCC | SubStructure | 20 | 25 | 30 | SubStructure | 90 | 95 | 40 | Landscape | 30 | 40 | 30
Rebar Works | SubStructure | 10 | 40 | 30 | SuperStructure | 0 | 60 | 60
Formworks | SubStructure | 30 | 40 | 15 | SuperStructure | 0 | 60 | 80 | Landscape | 60 | 80 | 5
PCC for RCC | SubStructure | 30 | 50 | 25 | SuperStructure | 0 | 60 | 70 | Landscape | 70 | 85 | 5
Masonary Works | SubStructure | 50 | 80 | 20 | SuperStructure | 50 | 80 | 60 | Landscape | 40 | 80 | 20
DPC Works | SubStructure | 95 | 100 | 100
Plaster Works | SubStructure | 80 | 90 | 10 | SuperStructure | 75 | 100 | 80 | Landscape | 70 | 90 | 10
Water Proofing Works | SubStructure | 90 | 95 | 25 | SuperStructure | 90 | 100 | 75
Screeding and Punninig (IPS Flooring) | SuperStructure | 85 | 100 | 100
Door Frame Installation Works | SuperStructure | 50 | 80 | 100
Window Installation | Finishing
Tile Works | Finishing | 0 | 50 | 90 | Landscape | 0 | 30 | 10
Marble Works | Finishing | 0 | 50 | 90 | Landscape | 0 | 30 | 10
Granite Works | Finishing | 0 | 50 | 90 | Landscape | 0 | 30 | 10
Stone Flooring Works | Finishing | 0 | 50 | 90 | Landscape | 0 | 30 | 10
Wooden Flooring Works | Finishing | 75 | 100 | 100
Paint Works | Finishing | 30 | 80 | 90 | Landscape | 30 | 80 | 10
Door Panel Installation | Finishing | 60 | 80 | 100
Electrical Conduiting | Utility and Servcies | 15 | 60 | 100
Electrical Wiriing | Utility and Servcies | 60 | 75 | 100
Electrical Fixtures | Utility and Servcies | 85 | 100 | 95 | Landscape | 50 | 100 | 5
Sanitary Pipe Fitting | Utility and Servcies | 30 | 50 | 85 | Landscape | 0 | 50 | 15
Sanitary Fixtures | Utility and Servcies | 85 | 100 | 95 | Landscape | 50 | 100 | 5
Staircase Railing Works | Finishing | 80 | 100 | 100
Iron Railing Works | Finishing | 80 | 100 | 100